## Sprint Story Board
To do - Backlog | Analysis (WIP:2) |  | Test Design (WIP:1) |  | Development (WIP:2) |  |  |  | Testing (WIP:1) |  |  | Ready for Prod | Deployed in Production
| In Progress | Done | In Progress | Done | Coding |  | Unit Test |  | Independent testing |  | SAT/UAT
[5 empty] | In Progress | Done | In Progress | Done (Ready for FQT) | In Progress | Done (Ready for Stage) | In Progress | Done
Generate report on injuries caused by medical devices from 2000-2015 | Analyze the story for technical and functional feasibility | 2015-06-19 | Generated queries for the reports, and tested them on FDA website | 2015-06-19 | Created HTML wireframes for the prototype screens. | 2015-06-20 | QUnit Test Scripts Created/executed | 2015-06-22 | Set up GitHub repository; craeted code base for the prototype. Set up OpenShift account for code deployment | 2015-06-22 |  | 2015-06-29 | 2015-07-06
Generate report on adverse effects caused by medical devices, reported by manyfacturers. | Communicate the analysis | 2015-06-23 | Test Scripts Peer Reviewed | 2015-06-24 | Coded web services calls for report queries to the FDA datasets |  | QUnit Test Complete | Ready to be Deployed to OpenShift | Test Validation Report Draft | 2015-06-23 | Tested first report | 2015-06-29 | 2015-07-06
Generate report on serious injusries caused by pacemakers |  |  | Review Test scripts with the Product Manager | 2015-06-24 | Coded web services calls for report queries to the FDA datasets Design Doc Created | 2015-06-24 |  |  | Targeted Regression Completed |  | Test Scripts executed and Passed | 06/29/2015 | 2015-07-06
Generate report on adverse effects caused by drugs used for treating Hypertension. |  |  |  |  | Coded web services calls for report queries to the FDA datasets |  |  |  | Test Scripts executed and Passed | 06/26/2015 |  | 6/29/2015 | 2015-07-06
Validated |  |  |  |  | Design Doc for technical approach created | 2015-06-29 |  |  |  |  | UAT Test Script Created | 2015-07-03
Document the agile process. |  |  | First Draft | 2015-11-29 | Doc Peer Review completed | 2015-06-30 |  |  |  |  | UAT Test Scripts executed and Passed | 2015-07-03 | 2015-07-06

## UAT-DeviceTimeBased
Project Name: Agile Delivery Services
Usability Test Case
Test Case ID: P2-1 |  |  |  | Test Designed by: | Ravi Kulkarni
Test Priority: 1 |  |  |  | Test Designed date: 06/27/2015
Module Name: |  |  |  | Test Executed by: Ravi Kulkarni
Test Title: Verify time based medical devices report |  |  |  | Test Execution date: 06/28/2015
Pre-condition: User has access to the internet and a browser
Dependencies: None
Step | Test Step |  | Test Data | Expected Result | Actual Result | Status
1 | Open any internet browser. |  | N/A
2 | Enter the URL: http://openfda-esciads.rhcloud.com/ |  | N/A | A default report (Device Reports - Time Based) is generated for injuried related to medical devices from 2000 to 2015. | A default report (Device Reports - Time Based) is generated for injuried related to medical devices from 2000 to 2015. | Pass
3 | Select the radio button "Reported by Consumers" |  | N/A | A report is generated for injuried related to medical devices, reported by consumers. | A report is generated for injuried related to medical devices, reported by consumers. | Pass
4 | Select the radio button "Reported for device 'PACEMAKER'" |  | N/A | A report is generated for injuried related to the medical device "PACEMAKER" | A report is generated for injuried related to the medical device "PACEMAKER" | Pass
Post-condition: The user has reviewed reports for injuries caused by medical devices, based on three different time based criteria.

## UAT-DeviceLocationBased
Project Name: Agile Delivery Services
Usability Test Case
Test Case ID: P2-2 |  |  |  | Test Designed by: | Ravi Kulkarni
Test Priority: 1 |  |  |  | Test Designed date: 06/27/2015
Module Name: |  |  |  | Test Executed by: Ravi Kulkarni
Test Title: Verify location based medical devices report |  |  |  | Test Execution date: 06/28/2015
Pre-condition: User has access to the internet and a browser. User has completed the test case P2-1. The browser displays the report generated for injuried related to the medical device "PACEMAKER".
Dependencies: None
Step | Test Step |  | Test Data | Expected Result | Actual Result | Status
1 | Click on the tab "Device Reports (Location Based)". |  | N/A | A default report is generated for all adverse events related to use of medical devices. | A default report is generated for all adverse events related to use of medical devices. | Pass
2 | Select the radio button "Reported location of event is patient's home". |  | N/A | A report is generated for injuried related to medical devices, that occurred at patients' homes. | A report is generated for injuried related to medical devices, that occurred at patients' homes. | Pass
3 | Select the radio button "Reported location of event is hospital". |  | N/A | A report is generated for injuried related to medical devices, that occurred at hospitals. | A report is generated for injuried related to medical devices, that occurred at hospitals. | Pass
Post-condition: The user has reviewed reports for injuries caused by medical devices, based on three different location based criteria.

## UAT-DeviceFrequencyBased
Project Name: Agile Delivery Services
Usability Test Case
Test Case ID: P2-3 |  |  |  | Test Designed by: | Ravi Kulkarni
Test Priority: 1 |  |  |  | Test Designed date: 06/27/2015
Module Name: |  |  |  | Test Executed by: Ravi Kulkarni
Test Title: Verify frequency based medical devices report |  |  |  | Test Execution date: 06/28/2015
Pre-condition: User has access to the internet and a browser. User has completed the test case P2-2. The browser displays the report generated for injuried related to the medical device "PACEMAKER".
Dependencies: None
Step | Test Step |  | Test Data | Expected Result | Actual Result | Status
1 | Click on the tab "Device Reports Frequency Based)". |  | N/A | A default report is generated for all adverse events related to use of medical devices, based on the frequencies of injuries caused. | A default report is generated for all adverse events related to use of medical devices, based on the frequencies of injuries caused. | Pass
2 | Select the radio button "Reported location of event is hospital". |  | N/A | A report is generated for all adverse events related to use of medical devices, that occurred in a hospital, based on the frequencies of injuries caused. | A report is generated for all adverse events related to use of medical devices, tat occurred in a hospital, based on the frequencies of injuries caused. | Pass
3 | Select the radio button "Device name includes hospital bed". |  | N/A | A report is generated for all adverse events related to use of a hospital bed, based on the frequencies of injuries caused. | A is generated for injuried related to medical devices, that occurred at hospitals. | Pass
Post-condition: The user has reviewed reports for injuries caused by medical devices, based on three different frequency based criteria.

## UAT-DrugReports
Project Name: Agile Delivery Services
Usability Test Case
Test Case ID: P2-4 |  |  |  | Test Designed by: | Ravi Kulkarni
Test Priority: 1 |  |  |  | Test Designed date: 06/27/2015
Module Name: |  |  |  | Test Executed by: Ravi Kulkarni
Test Title: Verify reports for adverse events related to drugs used for treating Hypertension. |  |  |  | Test Execution date: 06/28/2015
Pre-condition: User has access to the internet and a browser. User has completed the test case P2-3. The browser displays the report generated for all adverse events related to use of a hospital bed, based on the frequencies of injuries caused.
Dependencies: None
Step | Test Step |  | Test Data | Expected Result | Actual Result | Status
1 | Click on the tab "Drug Reports". |  | N/A | A default report is generated for adverse drug events, from 2004 to 2015, that included "Serious" reactions, specifically for treating hypertension. | A default report is generated for adverse drug events. From 2004 to 2015, that included "Serious" reactions, specifically for treating hypertension. | Pass
2 | Select the radio button "Reported by Manufacturers". |  | N/A | A report is generated for adverse drug events, from 2004 to 2015, that included "Serious" reactions, specifically for treating hypertension, and were reported by manufacturers. | A report is generated for adverse drug events, from 2004 to 2015, that included "Serious" reactions, specifically for treating hypertension, and were reported by manufacturers. | Pass
3 | Select the radio button "Reported by Consumers". |  | N/A | A report is generated for adverse drug events, from 2004 to 2015, that included "Serious" reactions, specifically for treating hypertension, and were reported by consumers. | A report is generated for adverse drug events, from 2004 to 2015, that included "Serious" reactions, specifically for treating hypertension, and were reported by consumers. | Pass
Post-condition: The user has reviewed reports for injuries caused by medical devices, based on three different frequency based criteria.